## Version 0.7.0
PlanetarySystemStacker: Development Roadmap
Feature | Description | Discussion | Author Responsible | Importance | Targeted for Version | Status
Rewriting of module "align_frame" | So far, the frame stabilization mode "surface" was implemented with local search algorithms which only worked well for very small search distances. As a consequence, big jumps between consecutive frames could not be handled well. The same problem affected the de-warping later in the processing workflow. There, the new "multi-level cross correlation" algorithm solved the problem. The same algorithm should be made available to the image stabilization. As a consequence, "surface" frame stabilization should become much more robust. | I have included the (internal) option "MultiLevelCorrelation" and made it the standard choice. First tests worked very well. I took this opportunity to streamline the implementation of modul "align_frame". It should work faster now when several alignment patches have to be tested before one can be used successfully. | Rolf | Must have | 0.7.0 | done
Shift video frame pixel values to fully use 16bit dynamic range | The metadata of SER videos often do not reflect the actual video data. In particular, the value "PixelDepthPerPlane" is often wrong for 16bit input, i.e. it is set to 16, but the video data only use the lower 8, 10 or 12 bit. If not corrected, the stacked output would alsmost be black. This kind of error needs to be detected automatically, and video data must be left-shifted by the appropriate amount of bits to fully use the dynamic range of 16 bits. | Add a method "correct_dynamic_range" to the SER parser. For 16bit input it determines the maximal pixel values in three frames (first, middle of video, last) during file opening, and the number of unused (high) bits. Later, when frames are read, the content is left-shifted by this number of bits. | Rolf | Must have | 0.7.0 | done
Frame brightness normalization | So far, only the related images (grayscale, Gauss, etc.) are normalized, such that the evaluation is not misled by brightness variations. Normalization should also be implemented for frame stacking. This will reduce blending artifacts. | The derived frame types should not be changed at all. Only the brightnesses are stored as a single value per frame. This will reduce compute times and limit clipping defects. Also, normalization should be made optional by adding GUI parameters. | Rolf | Must have | 0.7.0 | done
Implementation of Debayering in VideoReader | The selection of debayering patterns is alredy implemented in the GUI. It is passed to the VideoReader initialization via the instance variable "self.debayer_pattern". All supported patterns should be recognized and implemented in the read_frame method. Automatic detection of bayer matrices is implemented as well as the automatic detection of RGB channel ordering. | Is there anything still missing? | Rolf | Must have | 0.7.0 | done
Implementation of Debayering in ImageReader | The selection of debayering patterns is alredy implemented in the GUI. It is passed to the ImageReader initialization via the instance variable "self.debayer_pattern". All supported patterns should be recognized and implemented in the read_frame method. So far, the variable "self.debayer_pattern" is not used. | We assume that still image files are debayered already. | Rolf | Must have | 0.7.0 | done
Debayering during dark / flat file import | Applying a non-standard debayering pattern can be as useful for dark / flat frames as for the videos / image folders to be stacked. It is unclear how PSS treats the case when dark / flat frames are read from the file system. We need at least a clarification here, possibly also an addition in the SW. | We assume that still image files are debayered already. | Rolf | Must have | 0.7.0 | done
User Guide update | Update the user guide document. This includes: - Description of the workflow consistent with version 0.7.0 - Inclusion of new screenshots reflecting the GUI version 0.7.0 - Update of Appendix A reflecting current parameter definitions |  | Rolf | Must have | 0.7.0 | done
User Guide update (Appendix B) | Update Appendix B of the user guide document. The installation procedure for all supported Linux variants must be written in detail. Partially the information is given in the PSS discussion thread on "Cloudy Nights". Ideally, someone who experimented with the Linux installations would write this description. | I will start a discussion on Cloudy Nights to find someone to help with the details. | Rolf (plus John Duchek from the Cloudy Nights forum) | Must have | 0.7.0 | done
Algorithm documentation update | In document "algorithm_summary.docs": Change all descriptions of algorithms so that they reflect the SW version 0.7.0. Add a section on postprocessing. |  | Rolf | Must have | 0.7.0 | done
Add the option to use the "delete" key in the job editor instead of pressing the "remove selected job(s)" button explicitly | So far, when the user selects some job entries and presses the "del" key, nothing happens. This should be added as an alternative to using the "remove selected job(s)" key underneath the job list window. | Probably many users will expect this functionality to work. | Rolf | Nice to have | 0.7.0 | done
Automatic image brightness adjustment in frame viewers | Automatically adjust the image brightness in the frame viewers during the workflow (without changing the image content), so that the pixel values cover the entire dynamic range. | Simply spread the brightness distribution of pixels such that the minimum is zero and the maximum is 255. The method should work both for grayscale and color images. | Rolf | Nice to have | 0.7.0 | done
Add the option to save images in "png" format | So far only fits and tiff are supported. Png is another interesting lossless format. | The implementation should not be hard to do in method "save_image". | Rolf | Nice to have | 0.7.0 | done
Improve buffer handling | If more than one stacking job is executed in a row, data objects of the previous job are not freed consistently before starting the next one. When the next job starts, therefore, less RAM is available, so the job only runs at a lower buffering level than necessary. | References to large buffer objects must be reset in both the GUI and the workflow thread. Then the Python garbage collector must be forced to free those objects. | Rolf | Bug fix | 0.8.0 | done
Add the option to manually exclude frames from the input stack | This should be added as an additional phase (only in interactive mode) before the stack size is set. The GUI looks very similar to the stack size selection window. Instead of the Matplotlib window with frame qualities, a list of all frames is presented. The user can select / deselect frames in this list. | The implementation should be done in the module "frames" via an index translation table. This way (by going back to this step) frames can be restored by simply resetting the translation table. | Rolf | Must have | 0.8.0 | done
Add the option to start PSS via the command line | This way PSS could be integrated into larger workflows via shell scripting. The program should require one positional argument: a list of input files. Optional arguments are used to specify parameters. Missing optional arguments are replaced by standard values taken from the configuration currently active. | In this processing mode, "automatic" processing is switched on. In other words: There is no user interaction via a GUI possible. | Rolf | Must have | 0.8.0 | done
Add the support for "Drizzle" | This is helpful in the case of "undersampled" input material. The resolution of the stacked image is increased in both coordinate directions by a certain factor. A good choice of factors is 1.5, 2. and 3. | This feature requires sub-pixel resolution in the AP shift computations. Only the AP stacking buffers and the global buffer used to merge AB buffers need to be set to this higher resolution. | Rolf | Must have | > 0.8.0 | open
Add support for image derotation | If the frames were captured using an alt-azimuth mount, they must be de-rotated before stacking. | It must be decided if this feature fits well into the concept of PSS. It requires additional knowledge about the setting in which the frames were captured (such as the geographical location, the times when the frames were captured, and which object the telescope is aiming at). | Rolf | Nice to have | > 0.8.0 | open
Direct stacking of RAW color input | So far color material is de-bayered into three channel images immediately after reading. Stacking is then applied individually for all color channels. The alternative is to keep the 2D input and in the stacking process add the pixel values at the three different color locations to the apprpriately shifted locations of the corresponding stacking buffer channel. The statistical distribution of local shifts will guarantee that every pixel location receives data in all three colors. | This procedure requires to keep track of the number of stacking operations for each of the four different shift situations; i.e. in the end the stack is divided by four different counters, rather than the same value (the number of stacked images) as is the case now. | Rolf | Nice to have | > 0.8.0 | open
Add multi-size AP option | Especially in moon videos usually there are large areas with little structure (maria). With standard AP sizes this leads to large holes in the AP grid. Adding larger AP patches there manually is tedious. It would be nice if they could be added automatically. | This can be implemented either as multiple rounds of AP creation (with different sizes) or by adapting the AP creation process individually: If an AP creation fails because the structure or brightness condition is violated, PSS tries again using a larger AP size. This is continued (up to some threshold) until the AP conditions are fulfilled. | Rolf | Nice to have | > 0.8.0 | open
Add the frame stabilization mode "None" | Could be useful for input files which have been stabilized already with another tool, e.g., PIPP. | Michal: I see that this could be done to save some processing time. I don't think, however, that we really should do it. First of all, image stabilization is fast, so this would not save much CPU time. Second, we would rely on the quality of the external stabilization. Remaining inaccuracies would degrade the mean frame quality, and de-warping would be much harder to do. And then: If the video is already stabilized, another stabilization in PSS is very robust. The shifts are very small, and it is very unlikely that PSS would fail to detect them. Is there any other reason why you think this would be useful? | Rolf | Nice to have | > 0.8.0 | open
Add a histogram to the "rank frame " GUI | So far the "rank frame" GUI only shows the video frame together with a graphical representation of the quality graph. A histograph showing the brightness distribution of the video frame currently on display could be added underneath the quality graph. | Michal wrote: The implementation should be done using OpenCV which is said to be about 40x faster than np.histogram(). See: https://docs.opencv.org/3.1.0/d1/db7/tutorial_py_histogram_begins.html | Rolf | Nice to have | > 0.8.0 | open
Add a checkbox "Center the planet in frame after alligment" in the configuration dialog | Only for frame stabilization mode "Planet" The idea is to crop the dark space around a planet such that the planet appears centered in a (smaller) area than covered by the original frames. If the position of the planet moves during the video, the size of the box can only be determined after frame stabilization. This could be done by PSS automatically. | A very similar thing can be achieved (manually by the user) by selecting a ROI. The window presented there shows the "intersection" of all frames. The user only needs to draw a quadratic ROI around the planet there. A problem could be if (Jupiter) moons are in the frame. Should they be taken into account or not? To summarize, I'm not convinced yet that we should offer this option at all. | Rolf | Nice to have | > 0.8.0 | open
Add an option to add WinJuPos output file format | WinJuPos uses an input file name convention to associate files with the corresponding capture times. Since the output files from PSS can be used as input to WinJuPos, this option would help WinJuPos to interpret their times correctly. This is not trivial, because the result of a PSS stack resembles the scene as represented by the mean frame used. This frame, in turn, is the average of a set of individual frames of the input stack. The task here, therefore, is to compute the average time of all frames used in the mean frame computation. | This idea was broght forward by Tom Glenn on the Cloudy Nights forum. | Rolf | Nice to have | > 0.8.0 | open